## Sheet1
Imperial College Union 11.11.19
Site Survey completed by Karl Bott (Big City Consultants Ltd)
Area - main prep kitchen dining hall
| Observation | Accompanying Photo (if available) | Comments / Recommendations | Action Update | Stakeholder | Completion date
| Electrical Distribution board - very little detail recorded |  | The electrical distributution board should be labelled with the details of the appliances supplied from this unit | Complete Spie 19/11/2019 | Martin Benson | 2019-11-19
| Check if doors in catering areas are fire rated |  | It should be confirmed if / which of the kitchen doors are fire rated doors - once confirmed, a fire door notice should be displayed on both sides of the door | Logged | Martin Benson is this Jonothan Ryan?
| Intumescent strips missing on kitchen door |  | The missing / damaged intumescent strips on the kitchen door should be replaced | Logged 08/11/2019 | Martin Benson | Complete 19/11/2019
| Eggs stored on top shelf in fridge |  | Eggs should be stored on a low shelf in the fridge, below RTE food to prevent cross contamination | Kay Actioned and new signage produced awaiting deep clean to put out new signage and staff training before reopening | Kay Counter / Marvin Clarke | Complete 19/11/2019
| Vacpac machine - not labelled for either raw or Rte |  | The Vac Pac machine should only be used for either Raw OR RTE foods - it MUST not be used for both as this has a very high risk of cross contamination - the machine should be clearly labelled with the intanded use | Removed 24/11/2019 | Kay Counter | 2019-11-24
| Review temperature records - introduce new? |  | The current temperature records should be reviewed to confirm that they are adequate for the current offer - new records sheets should be introduced if required | New paperwork being assessed all in one sheet being split out to individual sheets | Kay Counter | 2019-11-23
| No designated raw prep area |  | A work area in the kitchen should be designated as a raw food preparation area and a Raw Food Preparation sign should be displayed for easy identification | New signage has been produced awaiting deep clean to put up | Kay Counter
| Cling film, foil & parchment not in wrap master dispensers |  | Cling film, foil & baking parchment should be stored in wrap master dispaensers to prevent cross contamination | Placed Nisbets order for wrapmasters - Marvin | Kay Counter/ Marvin Clarke | 2019-11-19
| Excessive extension sockets in use (poor condition) - 6 x double sockets - poorly positioned |  | It is recommended that the electrical sockets are repostioned to more suitable safe / useable locations | Complete Spie 19/11/2019 | Checked by Kay Counter | 2019-11-19
| Pedal bin damaged |  | The damaged pedal bin should be replaced | Placed Nisbets order for - Marvin | Kay Counter/ Marvin Clarke | 2019-11-19
| Spicy chicken in freezer past use by 6/11 |  | Out of date foods should be discarded - daily checks should be completed on food labelling to prevent food from exceeding the expiry date | Paperwork refreash and new labels purchased to prevent this and staff training | Kay Counter | Ongoing
| Raw burgers stored next to Rte foods in the freezer |  | Raw meat should be stored on the bottom shelf of the fridge, below RTE foods, to prevent cross contamination | New signage produced | Kay Counter | Ongoing
| Stilton in freezer not adequately covered |  | Food should be suitable covered during storage to prevent physical / cross contamination | culture change, training to be delivered before re opening | Kay Counter | Ongoing
| Bacon jam - final cooking / cooling records not available |  | Final cooking & cooling records must be completed when cooking / cooling high risk foods - these should be available for reference, to aid traceability checking in the event of a alleged food poisoning incident | paperwork split out into individual sheets raher than all in one | Kay Counter | Ongoing
| Base of can opener worn |  | The worn can openter blade should be replaced | will add to the list for relacement - Kay Marvin | Kay Counter / Marvin Clarke
| No dishwasher in place - equipment is not being sanitised during washing process |  | Equipment should be sanitised through the washing process using either heat (dishwasher) or chemical (sanitising solution) | introduced 3 stage washing process - including sanitisers Di | Kay Counter | Ongoing
| Raw & Rte chopping boards stored together in rack |  | Raw & RTE chopping boards should be stored seperately in racks to prevent cross contamination | New racks ordered from nisbets | Kay Counter / Marvin Clarke | 2019-11-19
| Opened packets of dry goods decanted - no allergen, batch code or bb4 date retained |  | Opened packets should be stored in sealed containers to prevent allergen contamination from spillages and to provide adequate pest proofing | Packets will be retained in sealed containers, staff training prior to reopening | Kay Counter | Ongoing
| Rational cleaning tabs - red & blue (sds & cra) - it was unclear if safety data sheets & chemical risk assessements are avaialble for the current chemicals on-site |  | Safety data sheets & chemical risk assessments should be available for all chemicals used on-site - Management & staff should know where these are stored, in the case of an emergency | safety data sheets, gained fom Diversey - printed off the risk assesments in folder in office assessment, staff are now going to sign to say they have been train ed on the chemicals being used | David Peskett | 2019-11-19
| Diversey chemicals in use |  | Disversey should be contacted to request a full site survery to provide the correct dosing equipment and COSHH training for the staff | Complete training being organised | Trish | Being organised dates TBC
| Damaged lobby brush |  | The damaged looby brush should be discarded / replaced | Complete order placed | Kay Counter / Marvin Clarke | 2019-11-19
| Pots /pans stored unsafely at side of stove |  | A suitable safe location to store pots & pans should be identified, as the current postion could potential result in burn related accidents | Reorgansation of the kitchen space will be addessed post deep clean | Kay Counter | Ongoing
| Fire extinguishers/ blanket inspected Nov 2018 - annual inspection due |  | The annual inspection of the fire extinguishers should be arranged, as this is due | Reported - 12.11.2019
| Cheese in freezer not labelled with a frozen on date |  | Food frozen in house should be labelled with a 'frozen on' & 'use by date' | New labels purchased staff trained | Kay Counter | Ongoing
| King prawns in freezer - not labelled with an opened on / use by date |  | Opened packets should be labelled with an opened on & use by date - following the manufacturers guidelines | New labels purchased staff trained | Kay Counter | Ongoing
| Fresh beef burgers stored in fridge in the original boxes from the butcher |  | Fresh Food deliveries should be removed from the packaging and stored in a sealed container and labelled with a use by date - following the manufacturers guidelines | New labels purchased staff trained | Kay Counter | Ongoing
| Redundant trailing cable from wall next to the oven |  | The redundant cable should be checked, isolated and removed if not required | Removed 19.11.2019 | Martin Benso | 2019-11-19
| Equipment servicing |  | It is recommended that a Planned Preventitive Maintenance (PPM) contract is taken out for the servicing of the catering equipment - to ensure equipment is safe to operate | first in service contacted for full assessment of goods and for maintenance contract | Kay Counter/Maria | Ongoing
Five Six Eight kitchen
| Observation | Accompanying Photo (if available) | Comments / Recommendations | To Be Actioned By |  | Completion date
| Split fridge door seals |  | Worn / damaged fridge / freezer door seals should be replaced, as this may negatively effect the internal temperature of the units | David contacted Gardaff - to come in and assess and fix | David Peskett/ Trish | Ongoing
| Disposables stored on the floor at entrance to the kitchen |  | Disposable food containers should be stored of the floor to prevent physical / cross contamination - Note. There is currently a cockroach issue in this area | created disposable aswell as a cleaning store so this is resolved | Kay Counter/ David Peskett | 2019-11-19
| Floor edging strip lifted - trip hazard |  | The raised floor edging strip should be removed and replaced as a priority, as this is a trip hazard in an area of high usage | Reported - 12.11.2019 | Martin Benson
| Fire door wedged open |  | Fire doors should be kept closed, if required to be open for practical reasons, a 'dorguard device' should be installed | Door guard device being fitted - martin benson | Martin Benson
| Build up of clutter in storage area e.g. dispo, fan, ladder, broom, |  | The area should be de-clutted, organised and maintained in a clean / tidy condition | Complete | Kay Counter/ David Peskett | 2019-11-19
| Saw stored on top of electric distribution board |  | The saw should be removed form the top of the electrical distribution board - return to the maintemnance department? |  | Kay Counter/ David Peskett | 2019-11-23
| Food stored on the floor in the walk-in freezer |  | Food should be stored off the floor to prevent physical / cross contamination | Will reorganise accordingly and pull onto pallet - 22.11.2019 | Kay Counter/ David Peskett | 2019-11-24
| Hand towel store on the floor in the fridge / storeroom |  | Hand towel should be stored off the floor to prevent physical / cross contamination | Now stored in disposable cupboard | Kay Counter/ David Peskett | 2019-11-19
| Chemical storeroom - no door, shelving rusty / damaged - walks damp damaged |  | The room used for storing chemicals should be reviwed, as this is currently in a very poor conditon - it is recommended that a tall metal cupboard is purchased, for the safe storage of chemicals | Added to maintenance list and chemicals reorganised into date order | Kay Counter/ David Peskett | 2019-11-19
| Metal scourers in use |  | It is recommended that scourers are not used, as these harbor food waste, bacteria and become rusty - the metal strands are also a known source of physical contamination due to falling off during washing & being left in the base of saucepans & being transferred into food | Removed 19.11.2019 | Kay Counter/ David Peskett | 2019-11-19
| Dead Cockroach in storage area |  | The pest contractor should be contacted ASAP to treat the area - the coackroach should be removed with dispoable paper towel & placed in the bin - the area should be cleaned and sanitised. Daily pest checks should be completed and documented - detailing evidence found and actions taken | Contractor contacted and spraying carried out - meeting with nic dent requested for long term strategy | Kay Counter/ Nic Dent | Awaiting preventative meeting ongoing
| First aid kit held together by cling film |  | The damaged first aid box should be replaced | New kit ordered | Kay Counter / Marvin Clarke | 2019-11-19
| Hazardous dishwasher chemical (corrosive) - spillage / chemical residue around lid & on cling film trailing from lid |  | The film covered in the corrosive chemical should be removed (using the correct PPE) - Staff should be trained of the safe use of chemicals under the COSHH regulations | Diversey contacted to review chemica coupling and staff training | Trish | Being organised dates TBC
| Worn chopping boards that cannot be effectively cleaned |  | Worn chopping boards boards should be replaced | Placed nisbets order - | Kay Counter / Marvin Clarke | 2019-11-19
| Probes - 2 x raw 2 Rte - unsure if calibrated |  | Temperature probes should be calibrated on a monthly basis, with the results recorded | probe calibration form now in circulation - 22.11.2019 | Kay Counter | Ongoing
| Scorched wall behind pizza oven |  | The damaged white rock wall surface should be repaired / replaced | Quote requested - Martin Benson 19/11/2019 | Martin Benson
| Electrical sockets positioned unsafely behind griddle plate |  | The electric sockets should be isolated and a cover plate installed to prevent the sockets from being used | Complete 19.11.2019 | Martin benson | 2019-11-19
| Loose door on the bottom microwave - possible microwave leaks - do not use |  | The microwave should be taken out of use, as there is a potential for microwave leaks from the damaged unit - repair or replace the microwave | Will remove this week 19.11.2019 | Kay Counter/ David Peskett | 2019-11-24
| Electric Fly Killer not working - not plugged in |  | The EFK should be plugged in and working at all times, to help prevent flying insects | new plug socket fitted - Complete | Martin benson | 2019-11-19
| Rusty magnetic knife rack |  | The rusty magnetic knife rack should be replaced - do not use this, as it is unfit to store knives on | New knife racks ordered for raw 1 for ready to eat | Kay Counter / Marvin Clarke | 2019-11-19
| Internal surfaces of undercounter freezer very dirty |  | The undercounter freezer should be deep cleaned, sanitised and maintained in a clean condition - check this is on the cleaning schedule | Ongoing but cleared for now | Trish | 2019-11-14
| Food uncovered in the u/c freezer |  | All food should be covered (& labelled) during storage to prevent allergen / physical / cross contamination | Ongoing but cleared for now | Trish | 2019-11-14
| Raw & RTE chopping boards stored together in rack |  | Raw and RTE choping boards should be stored seperately to prevent cross contamination | New chopping board stand ordered for raw/ ready to eat | Kay Counter / Marvin Clarke | 2019-11-19
| Raw chicken in undercounter fridge not labelled |  | All food should labelled with a use by date | Ongoing but cleared for now | Trish | 2019-11-14
| U/c fridge very dirty |  | The undercounter fridge should be deep cleaned, sanitised and maintained in a clean condition - check this is on the cleaning schedule | Ongoing but cleared for now | Trish | 2019-11-14
| Hand contact points on fridge, freezer door handles dirty |  | Hand contact points on fridge / freezer door handles should be regularly cleaned & sanitised throughout the day to prevent cross contamination | Ongoing but cleared for now | Trish | 2019-11-14
| Build up of pink bacterial residue in the dishwasher |  | The dishwasher should be regularly cleaned to prevent a build up of pink bacterial residue - check these are on a cleaning schedule | Diversey contacted to review chemical coupling and staff training | Trish | Being organised dates TBC
| Build up of dust on the ceiling ventilations grilles |  | The ceiling ventilation grilles should be regularly cleaned to prevent physical contamination | Added to cleaning schedule | Kay Counter | Ongoing
| Missing details on the HS Law poster |  | The required details on the HS Law poster should be completed | Will complete just confirming names | Kay Counter
| Build up of debris on the can opener blade |  | The can opener blade should be regularly cleaned to prevent a build up of debris | Added to cleaning schedule | Kay Counter | Ongoing
| Oil stored on the stairs in the storeroom |  | Stairways should be kept clear at all times to prevent trip hazards. Oil should be stored off the floor to prevent physical / cross contamination. Note. Cockroach found in the area | Complete | David Peskett/ Trish | 2019-11-14
| Cleaning items stored at the top of the stairway in the storeroom |  | The area at the top of the stairway should be cleared and kept clear / tidy | Complete | David Peskett/ Trish | 2019-11-14
| Significant build up food debris under hot lamps |  | The underside of the hot lamps at the hot plate should be cleaned and maintained in a cleaned condition - add to the cleaning schedule | Deep Clean ordered - new kit required as failed PAT test | Kay Counter / Marvin Clarke | awaiting quotes
| Extension leads used for fridges behind the bar |  | Extension sockets should be used as a temporary measure - request additional permanent sockets to be installed | New sockets requested - Martin Benson | Martin benson
| Chipped damaged shelving / shelf edges behind the bar |  | The damaged shelving / edging strips should be repaired / replaced | Reported - 12.11.2019 | Martin Benson
| Missing lids on hazardous dishwasher chemicals |  | Lids should be kept secure on hazardous chemicals during storage to prevent accidents from spillages | Diversey contacted to review chemical coupling and staff training | Trish | Being organised dates TBC
| Build up of scale / grime in the hand wash basins in the bar - damaged fittings & plug not available |  | The hand wash basin should be cleaned, sanitised and maintained in a clean condition - add to cleaning schedule, if required. The damaged fittings & missing plugs should be replaced |  | David Peskett/ Trish
| Cracked electric sockets under the bar |  | Replace cracked electrical sockets - these should not be used until they are safe to use | Reported - 12.11.2019 | Martin Benson
| Hand wash basin x 2,not designated - no signage in place |  | Hand wash basin only signage should be displayed at the hand wash basins | New signage printed and blue roll dispensers ordered | Kay Counter/ Marvin Clarke | 2019-11-19
| PAT testing out of date (2015) |  | PAT Testing should be completed as a priority in all of the areas to check that equipment is safe to use | PAT testing underway | Martin Benson | awaiting final report for Bar
| No paper towel available at the 2 hand wash basins |  | Paper towel should be available at all times to aid effective hand washing / drying - legal requirement | New signage printed and blue roll dispensers ordered | Kay Counter/ Marvin Clarke | 2019-11-19
| Soap missing from left hand side hand wash basin |  | Hand soap should be available at all times at the hand wash basins - legal requirement | Hand wash purchased | Trish | 2019-11-24
| Power supply cable on rear of bar not connected - no purpose |  | The redundant cable should be checked & if not required, removed | Reported - 12.11.2019 | Martin Benson
Union bar
| Observation | Accompanying Photo (if available) | Comments / Recommendations | To Be Actioned By |  | Completion date
| Fruit flies in bar area |  | The bar area should be thorougly cleaned to help to prevent fruit files - this includes under & behind fridges and shelving | Fly zapper - ordered for union bar | Kay Counter/ Marvin Clarke | 2019-11-19
| Damp damaged walls in cellar |  | The damaged walls in the cellar should be repaired / damp proofed | Reported - 12.11.2019 | Martin Benson
| Uncovered fruit in the cellar |  | Fruit should be stored in sealed containers to prevent fruit flies | Complete 22.11.2019 | Trish | 2019-11-22
| Leaking pipe in the cellar - water visibly running out of base of pipe |  | The leaking pipe should be repaired as a priority as water pooling on the cellar floor and is a slip hazard (& wasting water) | Complete 22.11.2019 | Martin Benson | 2019-11-22
| Knife stored in cellar |  | Knives should be stored safely when not in use | Complete | Kay Counter | 2019-11-23
| Risk assessments for ladder in cellar |  | A risk assessment should be completed for the steps in the cellar area | Karl completing - ongoing | Karl Bott
| Inspections completed for ladder in cellar |  | Weekly safety inspections should be completed & recorded for the steps in the cellar | Karl completing - ongoing - Ladder registration needs completing | Karl Bott
| Servicing of beer cradle |  | Check that regular servicing of the beer cradle is completed / documented | Investigating maintenance contract | Kay Counter
| Extension sockets under bar counter |  | Extension sockets should be used as a temporary measure - request additional permanent sockets are installed | New sockets requested - Martin Benson | Martin Benson
| Fire extinguisher not wall mounted / on stand |  | Fire extiguishers should be either wall mounted or stored on a stand - BS standard signage should be displayed for easy identification in the event of an emergency | Reported - 22.11.2019 | Unsure
Summary
The catering areas require attention to rectify non-compliance points in both Food Safety and Health & Safety
Key points requiring urgent attention are as follows: (see above for further details)
Food Safety
- Out of date food
- Dead Cockroach found in storage area in Five Six Eight
- Significant level of food uncovered in the Five Six Eight kitchen - which had been closed for almost a week previous to my visit
- Poor cleaning standards in the Five Six Eight kitchen - again, kitchen has not been open, so hard to understand why this has not been deep cleaned whilst closed
- Poor labelling practices
- Lack of hand washing facilities in the bar area e.g. soap & hand towel
-
Health & Safety | - Excessive / unsafe use of extension sockets in all areas
- PAT Testing out of date on a number of pieces of equipment
- Fire doors wedged open
- Unclear if doors in catering areas are fire doors
- Cracked / damaged electrical sockets in the bar
- Unsafe storage of chemicals